THE HOMEMADE PANTRY CO.

Business Launch Plan & Automation Stack

Jaime Kerber  |  jaimekerber@gmail.com  |  832-546-6446  |  www.homemadepantry.com

An elevated, intimate culinary experience — blending artisan baking, slow-living, and warm hospitality for small groups of up to 6 guests.

# PART 1: STEP-BY-STEP LAUNCH PLAN

Follow this sequence to go from idea to first paying guests in 30 days or less.

| STEP 1 | Lock In Your Legal & Financial Foundation (Week 1 — DO THIS FIRST) Register your business entity (LLC recommended for liability protection). Open a dedicated business bank account. Get a basic business liability insurance policy. This protects your home, personal assets, and guests. | ⏱ Timeline Days 1–5 |
| --- | --- | --- |

| STEP 2 | Define Your Offer & Pricing Set your per-person or per-event pricing. Consider: cost of supplies (sourdough, butter, jam, charcuterie), your time (3–3.5 hrs), hosting costs, and desired profit margin. Suggested starting range: $95–$150/person. Create 2–3 package tiers (e.g., Date Night, Girls Night, Private Event). | ⏱ Timeline Days 3–6 |
| --- | --- | --- |

| STEP 3 | Build Your Booking System Set up an online booking page (Calendly or HoneyBook). Create a simple intake form to capture: event type, group size, preferred dates, dietary restrictions. Link to your payment processor (Stripe or Square). Require a deposit (50%) at time of booking. | ⏱ Timeline Days 5–10 |
| --- | --- | --- |

| STEP 4 | Create Your Online Presence Build a simple website (Squarespace or Wix) with: your story, the experience description, pricing, booking link, and stunning photos. Set up Instagram (@homemadepantryco or similar). Create a Google Business Profile for local search visibility. | ⏱ Timeline Days 7–14 |
| --- | --- | --- |

| STEP 5 | Prep Your Space & Supplies Style your hosting area — clean, cozy, intentional. Stock: sourdough starter supplies, butter churns, jam jars, charcuterie boards, mason jars, printed recipe cards. Do a full practice run with friends/family to test the experience flow and timing. | ⏱ Timeline Days 10–18 |
| --- | --- | --- |

| STEP 6 | Soft Launch & First Bookings Invite 1–2 small groups (friends, neighbors, colleagues) for a free or discounted soft launch. Capture photos and video. Collect written testimonials. Use this content immediately for Instagram, your website, and word-of-mouth marketing. | ⏱ Timeline Days 15–22 |
| --- | --- | --- |

| STEP 7 | Marketing Push & Open Bookings Post your launch content on Instagram and Facebook. List on Eventbrite and Airbnb Experiences. Reach out to local businesses for corporate gifting partnerships. Turn on Google Ads or Facebook Ads with a small budget ($5–$10/day). Ask every guest to refer a friend. | ⏱ Timeline Days 20–30 |
| --- | --- | --- |

| STEP 8 | Review, Optimize & Scale After your first 5–10 events, review: what's working, what guests love, which packages are most popular. Adjust pricing, add dates, consider seasonal offerings. Explore hiring an assistant for prep work so you can take more bookings. | ⏱ Timeline Month 2+ |
| --- | --- | --- |

# PART 2: AUTOMATION STACK FOR BUSINESS TRACKING

The right tools will save you hours every week and ensure no booking, payment, or follow-up falls through the cracks.

CORE AUTOMATION STACK

| TOOL | PURPOSE | COST |
| --- | --- | --- |
| HoneyBook | All-in-one: bookings, contracts, invoices, client management, automations | ~$19/mo |
| Calendly | Online scheduling & calendar management (integrates with HoneyBook) | Free–$10/mo |
| Stripe | Payment processing — deposits, balances, refunds, automatic receipts | 2.9% + 30¢ |
| QuickBooks Simple | Bookkeeping, expense tracking, profit/loss reporting, tax prep | ~$20/mo |
| Google Workspace | Gmail, Drive, Sheets — store client data, receipts, templates | ~$6/mo |
| Later or Buffer | Schedule Instagram posts in advance; track engagement metrics | Free–$18/mo |
| Zapier | Connect all your tools — auto-trigger tasks between apps without coding | Free–$20/mo |
| Google Analytics | Track website traffic, where visitors come from, what converts | Free |

HOW THE AUTOMATION FLOWS

When a guest books through your website, here is what happens automatically:

- Guest visits your website and clicks the booking link → goes to Calendly

- Calendly shows available dates → guest selects a time and fills intake form

- HoneyBook auto-sends a booking contract for digital signature

- Stripe charges the 50% deposit automatically upon contract signing

- HoneyBook sends a confirmation email with event details and what to expect

- 2 days before the event, HoneyBook auto-sends a reminder email

- The day after the event, HoneyBook auto-sends a thank-you + review request

- QuickBooks automatically logs the payment and categorizes the income

- Zapier logs the new booking to a Google Sheet for your dashboard

YOUR BUSINESS DASHBOARD (Google Sheets — Free)

Build a simple Google Sheet to track your business at a glance. Track these columns:

- Date | Guest Name | Group Size | Package | Revenue | Deposit Received | Balance Due

- Monthly totals: Bookings, Revenue, Avg. Group Size, Top Package

- Expenses: Supplies, Marketing, Software subscriptions

- Net Profit by month

Zapier can automatically add a new row every time a booking is confirmed in HoneyBook.

ESTIMATED MONTHLY TECH COST

Total estimated monthly automation cost: $63–$93/month

This pays for itself with a single booking. At $120/person × 5 guests = $600/event.

# PART 3: YOUR FIRST 30 DAYS — ACTION CHECKLIST

| ✓ | ACTION ITEM | WEEK | OWNER |
| --- | --- | --- | --- |
| ☐ | Register LLC with Texas Secretary of State | Week 1 | Jaime |
| ☐ | Open business bank account | Week 1 | Jaime |
| ☐ | Get liability insurance quote | Week 1 | Jaime |
| ☐ | Sign up for HoneyBook + Stripe | Week 1 | Jaime |
| ☐ | Set up Calendly and connect to HoneyBook | Week 1 | Jaime |
| ☐ | Define packages and pricing | Week 1 | Jaime |
| ☐ | Build Squarespace or Wix website | Week 2 | Jaime |
| ☐ | Create Instagram account + first 9 posts | Week 2 | Jaime |
| ☐ | Set up Google Business Profile | Week 2 | Jaime |
| ☐ | Create email templates in HoneyBook (confirm, reminder, thank-you) | Week 2 | Jaime |
| ☐ | Set up QuickBooks + connect Stripe | Week 2 | Jaime |
| ☐ | Create Google Sheet dashboard + Zapier connection | Week 2 | Jaime |
| ☐ | Buy and prep all supplies for soft launch | Week 3 | Jaime |
| ☐ | Do 1–2 practice/soft launch events with friends | Week 3 | Jaime |
| ☐ | Collect photos, videos, testimonials from soft launch | Week 3 | Jaime |
| ☐ | Post launch content to Instagram + Facebook | Week 4 | Jaime |
| ☐ | List on Airbnb Experiences + Eventbrite | Week 4 | Jaime |
| ☐ | Send launch announcement email to personal contacts | Week 4 | Jaime |
| ☐ | Book your first 3 paying events | Week 4 | Jaime |

This is not just a baking class — it's a hosted culinary experience designed to feel cozy, intentional, and memorable. Now let's make it a business.